Research Focus 
Implementation of Edge Computing approaches to improve efficiency of Cloud Enterprise applications.

- Cloud Computing alone is too centralized to be truly efficient due to the latency of transferring massive data to a centralized repository

- A continuum that bridges the client to the cloud via Edge and Fog computing allows for greater distribution of resources, minimizing latency, economy of energy resources, expediting processes at the edge in order to transfer results to a secure habitat that will serve as a resource for machine learning algorithms to resource.

Applications

- Existing data processing algorithms are highly effective and necessary.  The results of those processes may be pushed to the cloud upon completion for storage.

- Machine Learning Algorithms may then be applied to draw highly specific conclusions from data repositories in the cloud to aid in automation of laboratory-side activities.

- A truly thin client, web API may not be sufficient to combat latency implemented on its own.  A lightweight client on an IOT device for data collection and laboratory-side access for those activities that cannot be automated such as routine maintenance.  Data is then transferred to cloud-based infrastructure for storage and analysis.

Articles

- https://www.networkworld.com/article/3224893/what-is-edge-computing-and-how-it-s-changing-the-network.html

- https://www.networkworld.com/article/3152800/predicting-the-end-of-cloud-computing.html

Process

- This work was inspired by the Linux Foundation.  The Linux Foundation has formed a five-project initiative to build an “interoperable, agnostic, open source edge computing framework” titled LFEdge.  It is the intention of the Linux Foundation to unify corporate efforts to push the boundary of current Edge Computing technology.

Background on the Linux Foundation and LFEdge mission can be read here:

https://www.linuxfoundation.org/press-release/2019/01/the-linux-foundation-launches-new-lf-edge-to-establish-a-unified-open-source-framework-for-the-edge/

https://www.lfedge.org/

- Another source of inspiration is Project EVE.  The Edge Virtualization Engine is one of the five projects under the umbrella of LFEdge.  Referred to as Project Eve, this is a hypervisor deployment that administers thin clients for edge devices.  The list of capabilities speaks directly to virtualized lab environments managing hardware from any distance with zero latency.

Back ground on Project Eve can be read here:

https://www.lfedge.org/projects/eve/

https://wiki.lfedge.org/display/EVE/Project+EVE

Open Source code for the hypervisor found on github here:

https://github.com/project-eve/eve/blob/master/README.md

Objectives

- Utilize SLIMS AWS in partnership with an Edge system designed on Arduino hardware to demonstrate how a highly complex laboratory ecosystem can be controlled by a lightweight Cloud implementation with an IoT gateway.

- Demonstrate networking outcomes as regards to overall speed of processes

- Demonstrate effectiveness of automation of laboratory-side activties

Scope 
Install Hardware:

Phase I: Automation of data collection via Slimsgate Plugin utilizing API interaction between Arduino Edge Module and VM

Phase II: Automation of laboratory-side activities via AI utilizes Raspberry Pi B+ in conjunction with Grove AI Hat

Install Software:

Phase I: SLIMS on a Windows 2019 VM on an Antsle XD Ultra

Phase II:  SLIMS AWS

Streamline overall process:

decrease latency with file transfer in virtualized networks

increase automation reliability via algorithm

Timeframe

|  | Description of Work | Start and End Dates |
| --- | --- | --- |
| Phase One | Infrastructure - Aeroponics Lab Design and Build - Edge Module Design and Build - Spin up SLIMS VM with Dependencies | Late Spring and Summer – May thru September |
| Phase Two | Software Development and Testing - Code Edge Module Implementation - C++ - Code API Plugin - Java - Validation Plan Implementation | Early Fall - October thru November |
| Phase Three | Laboratory Testing - Confirm hardware/software module in situ at SWT Aeroponics Lab in Greensboro, NC - Write Up Conclusions | Late Fall - November thru first week of December |

Project Budget

|  | Description of Work | Anticipated Costs |
| --- | --- | --- |
| Phase One | Infrastructure | Substantial |
| Phase Two | Software Development and Testing | Negligible |
| Phase Three | Laboratory Testing | Negligible |
|  | Total | $ 0.00 |

Key Stakeholders

| Project Sponsor | Lisa Buurma, Agilent Technologies LSAG Software Informatics Division |
| --- | --- |
| Project Advisor | Gregg Vesonder, Industry Professor and Director, Research, Systems and Software Division |
| Project Researcher | Fran Sabetpour, Sabetpour Wingate Technologies |
| Project Researcher | Anthem Wingate, Sabetpour Wingate Technologies |

Monitoring and Evaluation 
Phase One: Completion confirmed upon successful hardware implementation.  This includes installation of the Aeroponics Laboratory, the Edge Module, and SLIMS VM.

Phase Two:  Completion confirmed upon code review and implementation of validation plan.  Refactor as necessary.

Phase Three:  Completion confirmed via collection of Aeroponics data with additional focus on data transfer speeds..

Approval Signatures

| Fran Sabetpour, Project Researcher |  | Lisa Buurma, Project Sponsor |  |
| --- | --- | --- | --- |

| Anthem Wingate, Project Researcher |  | Gregg Vesonder, Project Advisor |  |
| --- | --- | --- | --- |